## Tasks
Phase | Priority | Category | Task | Timeline | Notes | Status
PHASE 1 | 🚨 CRITICAL | Spam Removal | Backup entire site before making changes | Week 1 | Do first before anything | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Check GSC for Manual Actions and Security Issues | Week 1 | Login to Search Console | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Change all WordPress admin passwords | Week 1 | Use strong passwords | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Change hosting control panel password | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Change FTP/SFTP passwords | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Scan for malware using security plugin | Week 1 | Install Wordfence or Sucuri first | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Search server for files containing: ?e=, shop.php, jp.php, article.php, goods.php, pin.php | Week 1 | Use SSH/FTP file search | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Search for Japanese/Chinese encoded strings in files | Week 1 | Look for: Dynabook, YONEX, Panasonic | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Delete all spam files from server | Week 1 | Make list first, then delete | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Clean database of spam entries | Week 1 | Check wp_posts, wp_postmeta tables | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Verify no backdoor/malware files remain | Week 1 | Check wp-config.php, .htaccess | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Configure 410 Gone responses for spam URLs in .htaccess | Week 1-2 | Add RewriteCond rules | TRUE
PHASE 1 | 🚨 CRITICAL | Spam Removal | Update robots.txt to temporarily block spam patterns | Week 1-2 | Block: /?e=, /*?e=, /jp.php, /shop.php, /article.php | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Update WordPress core to latest version | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Update all plugins to latest versions | Week 1 | Check for vulnerable plugins | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Update theme to latest version | Week 1 | Jannah theme | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Remove unused/suspicious plugins | Week 1 | Audit all installed plugins | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Install security plugin (Wordfence or Sucuri) | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Enable two-factor authentication | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Check file permissions (755 for directories, 644 for files) | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Security | Review all user accounts and remove suspicious ones | Week 1 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Technical | Remove noindex tag from /simulation/ | Week 1-2 |  | FALSE
PHASE 1 | 🚨 CRITICAL | Technical | Remove noindex tag from /how-to-search-research-paper/ | Week 1-2 |  | FALSE
PHASE 1 | 🚨 CRITICAL | Technical | Remove noindex from all core service pages | Week 1-2 | Keep noindex on: wp-login, wp-admin, search, tags | FALSE
PHASE 1 | 🚨 CRITICAL | Technical | Unblock CSS in robots.txt: /wp-content/themes/jannah/*.css | Week 1-2 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Technical | Unblock JavaScript files needed for rendering | Week 1-2 |  | TRUE
PHASE 1 | 🚨 CRITICAL | Technical | Test robots.txt with Google Search Console Robots Tester | Week 2 | After making changes | TRUE
PHASE 1 | 🚨 CRITICAL | Technical | Fix broken link: /assignments/ - Create page or 301 redirect | Week 1-2 | Linked from multiple pages | FALSE
PHASE 1 | 🚨 CRITICAL | Technical | Fix broken link: /isi-paper/ | Week 1-2 |  | FALSE
PHASE 1 | 🚨 CRITICAL | Technical | Upload missing images: /wp-content/uploads/2024/10/Screenshot-*.png | Week 1-2 | Or remove references | FALSE
PHASE 1 | 🚨 CRITICAL | GSC Actions | Submit Disavow File for spam domains: vipan.xyz (78% spam) | Week 2 |  | TRUE
PHASE 1 | 🚨 CRITICAL | GSC Actions | Submit Disavow File for: italyyt.xyz (67% spam) | Week 2 |  | TRUE
PHASE 1 | 🚨 CRITICAL | GSC Actions | Disavow all domains with spam score >50% | Week 2 | Create disavow.txt file | TRUE
PHASE 2 | ⚠️ HIGH | Redirects | Run Screaming Frog to identify all redirect chains | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Redirects | Fix redirect: /2023/05/ (301 to itself) | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Redirects | Fix redirect: /2024/12/ (redirecting to home) | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Redirects | Convert archive page redirects to proper pagination | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Redirects | Update internal links to point directly to final URLs | Week 3-4 | Avoid redirect chains | FALSE
PHASE 2 | ⚠️ HIGH | Canonical | Add self-referential canonical tags to all legitimate pages | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Canonical | Fix non-200 canonical URLs | Week 3 | Check audit data | FALSE
PHASE 2 | ⚠️ HIGH | Canonical | Verify www vs non-www consistency | Week 3 | Choose one version | FALSE
PHASE 2 | ⚠️ HIGH | Canonical | Check for canonical-noindex conflicts | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Generate new XML sitemap with ONLY legitimate pages | Week 3 | Exclude all spam URLs | TRUE
PHASE 2 | ⚠️ HIGH | Sitemap | Include homepage in sitemap | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Include main service pages in sitemap | Week 3 | انجام پایان نامه, پروپوزال, etc. | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Include legitimate blog posts in sitemap | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Include static pages (About, Contact) in sitemap | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Submit XML sitemap to Google Search Console | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Sitemap | Submit XML sitemap to Bing Webmaster Tools | Week 3 |  | FALSE
PHASE 2 | ⚠️ HIGH | Meta Data | Add title to: /research-sevices/writing-thesis/ | Week 3-4 | انجام پایان نامه ¦ خدمات نگارش پایان‌نامه | FALSE
PHASE 2 | ⚠️ HIGH | Meta Data | Add title to: /research-sevices/writing-proposal/ | Week 3-4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Meta Data | Add title to: /how-to-write-thesis/ | Week 3-4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Meta Data | Fix all empty titles identified in Moz report | Week 3-4 | 50-60 characters each | FALSE
PHASE 2 | ⚠️ HIGH | Meta Data | Add meta descriptions to all pages (150-160 chars) | Week 3-4 | Include target keywords | FALSE
PHASE 2 | ⚠️ HIGH | Images | Add alt text to logo (already done: موسسه تزنویسان) | Week 3-4 | Verify | FALSE
PHASE 2 | ⚠️ HIGH | Images | Add alt texts to hypothesis images | Week 3-4 | Example: فرضیه علی در پژوهش | FALSE
PHASE 2 | ⚠️ HIGH | Images | Add alt texts to all service page images | Week 3-4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Images | Add alt texts to all blog post images | Week 3-4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Images | Add alt texts to screenshots and diagrams | Week 3-4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Internal Links | Review homepage internal links (71 links) | Week 4 | Quality check | FALSE
PHASE 2 | ⚠️ HIGH | Internal Links | Add contextual links to depth 3-4 pages | Week 4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Internal Links | Use descriptive anchor text (not just کلیک کنید) | Week 4 |  | FALSE
PHASE 2 | ⚠️ HIGH | Internal Links | Link from high-authority pages to service pages | Week 4 |  | FALSE
PHASE 3 | 📊 MEDIUM | Content | Identify thin content pages (low word count) | Week 5 | Use audit data | FALSE
PHASE 3 | 📊 MEDIUM | Content | Expand service pages to minimum 1,000 words | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Content | Update truncated meta descriptions | Week 5 |  | FALSE
PHASE 3 | 📊 MEDIUM | Content | Add proper heading structure (H1, H2, H3) to all pages | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Content | Ensure H1 matches page topic and includes keyword | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Indexing | Request indexing via GSC for homepage | Week 5 | After spam cleanup | FALSE
PHASE 3 | 📊 MEDIUM | Indexing | Request indexing for top 20 service pages | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Indexing | Request indexing for recent blog posts (last 3 months) | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Indexing | Monitor 'Crawled - currently not indexed' in GSC | Week 5-6 | Check weekly | FALSE
PHASE 3 | 📊 MEDIUM | Indexing | Check for duplicate content issues | Week 5-6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Technical | Fix Soft 404s (2 pages identified) | Week 5 | Return proper 404 or fix content | FALSE
PHASE 3 | 📊 MEDIUM | Technical | Fix Server errors 5xx (102 pages) | Week 5-6 | Check error logs | FALSE
PHASE 3 | 📊 MEDIUM | Technical | Fix Blocked due to 4xx (749 pages) | Week 5-6 | Review and resolve | FALSE
PHASE 3 | 📊 MEDIUM | Technical | Fix Duplicate without canonical (266 pages) | Week 5-6 | Add proper canonicals | FALSE
PHASE 3 | 📊 MEDIUM | Mobile | Test mobile-friendliness in GSC | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Mobile | Fix any mobile usability issues | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Mobile | Verify responsive design works properly | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Mobile | Test loading speed on mobile (target: <3 seconds) | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Run Google PageSpeed Insights | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Compress images (convert to WebP format) | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Enable browser caching | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Minify CSS/JS files | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Enable GZIP compression | Week 6 |  | FALSE
PHASE 3 | 📊 MEDIUM | Speed | Consider CDN for static assets | Week 6 |  | FALSE
PHASE 4 | 🔗 BACKLINKS | Analysis | Review teznevisan7.com backlinks (999 linking pages) | Week 7 | Is this your domain or competitor? | FALSE
PHASE 4 | 🔗 BACKLINKS | Analysis | If competitor: File DMCA for copied content | Week 7 |  | FALSE
PHASE 4 | 🔗 BACKLINKS | Analysis | If your domain: Implement proper 301 redirects | Week 7 |  | FALSE
PHASE 4 | 🔗 BACKLINKS | Disavow | Create disavow.txt file with all spam domains | Week 7 | domain:vipan.xyz format | TRUE
PHASE 4 | 🔗 BACKLINKS | Disavow | Add cplusplus.com links if spammy context (35% spam) | Week 7 | Review individual links | TRUE
PHASE 4 | 🔗 BACKLINKS | Disavow | Add pointblog.net suspicious links (25% spam) | Week 7 |  | TRUE
PHASE 4 | 🔗 BACKLINKS | Disavow | Upload disavow file to Google Search Console | Week 7 | Disavow Links tool | TRUE
PHASE 4 | 🔗 BACKLINKS | Preservation | Verify behance.net backlink is active (DA 93, 1% spam) | Week 8 |  | FALSE
PHASE 4 | 🔗 BACKLINKS | Preservation | Verify linkedin.com backlink is active | Week 8 |  | TRUE
PHASE 4 | 🔗 BACKLINKS | Preservation | Verify medium.com backlink is active | Week 8 |  | FALSE
PHASE 4 | 🔗 BACKLINKS | Preservation | Verify crunchbase.com backlink is active | Week 8 |  | TRUE
PHASE 4 | 🔗 BACKLINKS | Preservation | Ensure target pages for quality backlinks remain active | Week 8 |  | FALSE
PHASE 5 | 📈 MONITORING | GSC | Track 'Indexed' vs 'Not indexed' daily | Week 9-12 | Set up daily alert | FALSE
PHASE 5 | 📈 MONITORING | GSC | Monitor crawl stats for 200 OK response improvement | Week 9-12 | Target: >80% vs current 11.6% | FALSE
PHASE 5 | 📈 MONITORING | GSC | Check for new coverage errors weekly | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | GSC | Track impressions and clicks growth | Week 9-12 | Current: 45 clicks in 23 months | FALSE
PHASE 5 | 📈 MONITORING | GSC | Monitor Core Web Vitals | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: تزنویسان (current position 4.6) | Week 9-12 | Target: Top 3 | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: موسسه تزنویسان (current position 1.5) | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: انجام پایان نامه (current position 4.1, 0 clicks) | Week 9-12 | PRIORITY KEYWORD | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: موسسه تز نویسان | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: پایان نامه | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: مشاوره پایان نامه | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: تحلیل آماری | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Rankings | Track: انجام پروپوزال | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Analytics | Set up Google Analytics properly | Week 9 | If not already done | FALSE
PHASE 5 | 📈 MONITORING | Analytics | Track organic traffic weekly | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Analytics | Monitor bounce rate and engagement | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Analytics | Track conversions (form submissions, contacts) | Week 9-12 |  | FALSE
PHASE 5 | 📈 MONITORING | Competition | Research competitors ranking for انجام پایان نامه | Week 10 |  | FALSE
PHASE 5 | 📈 MONITORING | Competition | Analyze competitor content structure | Week 10 |  | FALSE
PHASE 5 | 📈 MONITORING | Competition | Identify keyword gaps | Week 10 | Use Ahrefs | FALSE
PHASE 5 | 📈 MONITORING | Competition | Review competitor backlink profiles | Week 10 |  | FALSE
PHASE 6 | 🚀 GROWTH | Link Building | Guest posting on Iranian academic blogs | Month 4+ |  | FALSE
PHASE 6 | 🚀 GROWTH | Link Building | Partnerships with university resources | Month 4+ |  | FALSE
PHASE 6 | 🚀 GROWTH | Link Building | Relevant directory submissions only | Month 4+ | No spam directories | FALSE
PHASE 6 | 🚀 GROWTH | Link Building | Complete and activate social media profiles | Month 4 |  | FALSE
PHASE 6 | 🚀 GROWTH | Local SEO | Create/optimize Google Business Profile | Month 4 | If applicable | FALSE
PHASE 6 | 🚀 GROWTH | Local SEO | Add accurate location information | Month 4 |  | FALSE
PHASE 6 | 🚀 GROWTH | Local SEO | Collect customer reviews | Month 4+ |  | FALSE
PHASE 6 | 🚀 GROWTH | Local SEO | Add schema markup for local business | Month 4 |  | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to homepage (ID: 46) | Week 1 | Design hero image | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to 'درباره موسسه' (ID: 57) | Week 1 | About page photo | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to 'ثبت شکایت' (ID: 2129) | Week 1 | Complaint form | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to 'تماس با تزنویسان' (ID: 1916) | Week 1 | Contact design | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to 'فرصت های شغلی' (ID: 60) | Week 1 | Career image | FALSE
CONTENT | 🎨 IMAGES | Featured | Add featured image to 'خط مشی حریم خصوصی' (ID: 1460) | Week 1 | Privacy icon | FALSE
CONTENT | 🎨 IMAGES | Featured | Create 20 featured images for posts without images | Week 1-2 | Academic themes | FALSE
CONTENT | 🎨 IMAGES | Featured | Create 33 featured images for pages without images | Week 2-3 | Service designs | FALSE
CONTENT | 🎨 IMAGES | Standards | Establish featured image size (1200x630px) | Week 1 | Social sharing | FALSE
CONTENT | 🎨 IMAGES | Standards | Create featured image template in Canva | Week 1 | Brand consistency | FALSE
CONTENT | 📊 SEO | Scores | Optimize 41 posts with Yoast scores <50 | Week 2-4 | Target: 70+ | FALSE
CONTENT | 📊 SEO | Scores | Optimize 69 posts with RankMath scores <50 | Week 2-4 | Target: 60+ | FALSE
CONTENT | 📊 SEO | Scores | Export list of posts with SEO scores <30 | Week 2 | Worst performers | FALSE
CONTENT | 📊 SEO | Keywords | Add focus keywords via Yoast/RankMath | Week 3 | One per post | FALSE
CONTENT | 📊 SEO | Readability | Improve readability (subheadings, short paragraphs) | Week 3-4 | Persian language | FALSE
CONTENT | ✍️ EXCERPTS | Posts | Write excerpts: 'آموزش روش تحقیق' (11 posts) | Week 2 | 120-160 chars | FALSE
CONTENT | ✍️ EXCERPTS | Posts | Write excerpts: 'انجام شبیه سازی' (11 posts) | Week 2 | 120-160 chars | FALSE
CONTENT | ✍️ EXCERPTS | Posts | Write excerpts: 'انجام پایان نامه' (9 posts) | Week 2-3 | 120-160 chars | FALSE
CONTENT | ✍️ EXCERPTS | Posts | Write excerpts: 'آموزش پایان نامه' (7 posts) | Week 3 | 120-160 chars | FALSE
CONTENT | ✍️ EXCERPTS | Posts | Write excerpts for remaining 6 posts | Week 3 | All 28 posts | FALSE
CONTENT | ✍️ EXCERPTS | Quality | Ensure excerpts include target keyword | Week 3 | Natural placement | FALSE
CONTENT | ✍️ EXCERPTS | Quality | Ensure excerpts are compelling CTAs | Week 3 | Encourage clicks | FALSE
CONTENT | 📝 DRAFTS | Review | Audit all 28 draft posts for quality | Week 3 | Completeness check | FALSE
CONTENT | 📝 DRAFTS | Review | Identify top 10 priority drafts | Week 3 | Keyword opportunity | FALSE
CONTENT | 📝 DRAFTS | Optimize | Add featured images to all drafts | Week 3-4 | 28 images needed | FALSE
CONTENT | 📝 DRAFTS | Optimize | Add meta titles to all drafts | Week 3-4 | 50-60 chars + keyword | FALSE
CONTENT | 📝 DRAFTS | Optimize | Add meta descriptions to all drafts | Week 3-4 | 150-160 chars | FALSE
CONTENT | 📝 DRAFTS | Optimize | Add excerpts to all drafts | Week 3-4 | 120-160 chars | FALSE
CONTENT | 📝 DRAFTS | Optimize | Fix heading structure in drafts | Week 4 | H1, H2, H3 | FALSE
CONTENT | 📝 DRAFTS | Publish | Publish 5 highest-priority drafts | Week 4 | After optimization | FALSE
CONTENT | 📝 DRAFTS | Publish | Publish 5 more drafts | Week 5 | Stagger indexing | FALSE
CONTENT | 📝 DRAFTS | Publish | Publish remaining 18 drafts | Week 6-8 | 2-3 per week | FALSE
CONTENT | 📝 DRAFTS | GSC | Request indexing for each new post | Week 4-8 | Via GSC | FALSE
CONTENT | 🏗️ STRUCTURE | Headings | Audit H1 tags on all 48 pages | Week 4 | One H1 per page | FALSE
CONTENT | 🏗️ STRUCTURE | Headings | Add H2 every 300-400 words | Week 4-5 | Readability + SEO | FALSE
CONTENT | 🏗️ STRUCTURE | Headings | Use H3 for sub-sections | Week 4-5 | Proper hierarchy | FALSE
CONTENT | 🏗️ STRUCTURE | Paragraphs | Break long paragraphs (>5 lines) | Week 5 | Persian readability | FALSE
CONTENT | 🏗️ STRUCTURE | Lists | Convert dense text to bullet points | Week 5 | Steps, features | FALSE
CONTENT | 🏗️ STRUCTURE | Tables | Add tables for pricing comparisons | Week 5 | Visual clarity | FALSE
CONTENT | 🏗️ STRUCTURE | CTAs | Add CTAs at end of each post | Week 5 | Contact form link | FALSE
CONTENT | 🎯 KEYWORDS | Research | Research: 'انجام پایان نامه' | Week 3 | Long-tail variations | FALSE
CONTENT | 🎯 KEYWORDS | Research | Research: 'تحلیل آماری SPSS' | Week 3 | Tutorial keywords | FALSE
CONTENT | 🎯 KEYWORDS | Research | Research: 'مشاوره پایان نامه' | Week 3 | Consulting keywords | FALSE
CONTENT | 🎯 KEYWORDS | Mapping | Create keyword map for all 48 pages | Week 3 | One primary each | FALSE
CONTENT | 🎯 KEYWORDS | Optimize | Add keywords to titles (first 5 words) | Week 4 | All pages | FALSE
CONTENT | 🎯 KEYWORDS | Optimize | Add keywords to first paragraph | Week 4 | Natural placement | FALSE
CONTENT | 🎯 KEYWORDS | Optimize | Add keyword variations throughout | Week 4-5 | No stuffing | FALSE
CONTENT | 🎯 KEYWORDS | Optimize | Add keywords to image filenames | Week 5 | Not IMG001.jpg | FALSE
CONTENT | 📚 PILLAR | Plan | Outline: 'راهنمای کامل انجام پایان نامه' | Week 5 | 2,500+ words | FALSE
CONTENT | 📚 PILLAR | Write | Introduction & Overview | Week 6 | What is thesis | FALSE
CONTENT | 📚 PILLAR | Write | Chapter 1 guide (Problem statement) | Week 6 |  | FALSE
CONTENT | 📚 PILLAR | Write | Chapter 2 guide (Literature review) | Week 6 |  | FALSE
CONTENT | 📚 PILLAR | Write | Chapter 3 guide (Methodology) | Week 6 |  | FALSE
CONTENT | 📚 PILLAR | Write | Chapter 4 guide (Analysis) | Week 6 |  | FALSE
CONTENT | 📚 PILLAR | Write | Chapter 5 guide (Conclusions) | Week 6 |  | FALSE
CONTENT | 📚 PILLAR | Write | FAQ section | Week 7 | 10+ questions | FALSE
CONTENT | 📚 PILLAR | Optimize | Add table of contents | Week 7 | Jump links | FALSE
CONTENT | 📚 PILLAR | Optimize | Add internal links to related posts | Week 7 | Services + tutorials | FALSE
CONTENT | 📚 PILLAR | Publish | Publish with full optimization | Week 7 | Image, schema, etc | FALSE
CONTENT | 🌐 CLUSTER | Thesis | Write: 'انتخاب موضوع پایان نامه' | Week 7 | 1,200+ words | FALSE
CONTENT | 🌐 CLUSTER | Thesis | Write: 'نگارش فصل اول' | Week 8 | 1,200+ words | FALSE
CONTENT | 🌐 CLUSTER | Thesis | Write: 'روش تحقیق' | Week 8 | 1,200+ words | FALSE
CONTENT | 🌐 CLUSTER | Thesis | Write: 'تحلیل داده با SPSS' | Week 8 | 1,500+ with screenshots | FALSE
CONTENT | 🌐 CLUSTER | Thesis | Write: 'آماده سازی دفاع' | Week 9 | 1,200+ words | FALSE
CONTENT | 🌐 CLUSTER | Proposal | Write: 'پروپوزال دکتری' | Week 9 | 1,200+ words | FALSE
CONTENT | 🌐 CLUSTER | Proposal | Write: 'تفاوت پروپوزال ارشد و دکتری' | Week 9 | 1,000+ words | FALSE
CONTENT | 🌐 CLUSTER | Stats | Write: 'آموزش AMOS' | Week 10 | 1,500+ tutorial | FALSE
CONTENT | 🌐 CLUSTER | Stats | Write: 'آموزش EViews' | Week 10 | 1,500+ tutorial | FALSE
CONTENT | 🌐 CLUSTER | Links | Link all cluster to pillar | Week 10 | Bidirectional | FALSE
CONTENT | 🔄 UPDATES | Refresh | Update dates for stale content (>1 year) | Week 6 | Add 'Updated: Feb 2026' | FALSE
CONTENT | 🔄 UPDATES | Refresh | Update statistics in old posts | Week 6-7 | Pricing, tools, trends | FALSE
CONTENT | 🔄 UPDATES | Refresh | Expand top 10 posts by traffic | Week 7 | Add new sections | FALSE
CONTENT | 🔄 UPDATES | Refresh | Fix outdated screenshots | Week 7 | SPSS, AMOS interfaces | FALSE
CONTENT | 🔄 UPDATES | Refresh | Replace broken external links | Week 7 | Current resources | FALSE
CONTENT | 🔖 SCHEMA | Article | Add Article schema to blog posts | Week 8 | JSON-LD | FALSE
CONTENT | 🔖 SCHEMA | FAQ | Add FAQ schema to pillar | Week 8 | 10+ questions | FALSE
CONTENT | 🔖 SCHEMA | Service | Add Service schema to service pages | Week 8 | Thesis, Proposal, Analysis | FALSE
CONTENT | 🔖 SCHEMA | HowTo | Add HowTo schema to tutorials | Week 9 | Step-by-step | FALSE
CONTENT | 🔖 SCHEMA | Review | Add Review schema to testimonials | Week 9 | AggregateRating | FALSE
CONTENT | 🔖 SCHEMA | Organization | Add Organization schema to About | Week 9 | Contact, socials | FALSE
CONTENT | 🔖 SCHEMA | Breadcrumb | Add Breadcrumb schema to all pages | Week 9 | SERP appearance | FALSE
CONTENT | 🔖 SCHEMA | Test | Test schema with Rich Results Test | Week 9 | Fix errors | FALSE
CONTENT | 🎬 MEDIA | Graphics | Create infographics for methodology | Week 10 | Visual aids | FALSE
CONTENT | 🎬 MEDIA | Graphics | Create flowcharts for thesis process | Week 10 | Chapter flow | FALSE
CONTENT | 🎬 MEDIA | Graphics | Create comparison tables as images | Week 10 | Shareable | FALSE
CONTENT | 🎬 MEDIA | Video | Video: 'آموزش SPSS' (optional) | Month 4+ | If resources allow | FALSE
CONTENT | 🎬 MEDIA | Video | Video: 'معرفی خدمات' (optional) | Month 4+ | Homepage hero | FALSE
CONTENT | 📅 CALENDAR | Plan | Create 3-month content calendar | Week 8 | Topics, keywords, dates | FALSE
CONTENT | 📅 CALENDAR | Plan | Schedule 2 posts/week for 12 weeks | Week 8 | Consistent publishing | FALSE
CONTENT | 📅 CALENDAR | Plan | Plan seasonal content | Week 8 | Academic cycles | FALSE
CONTENT | 📅 CALENDAR | Plan | Assign keywords to planned posts | Week 8 | Keyword strategy | FALSE
CONTENT | ✅ QA | Proofread | Proofread all 28 published posts | Week 5 | Grammar/spelling | FALSE
CONTENT | ✅ QA | Proofread | Proofread all 48 pages | Week 6 | Professional tone | FALSE
CONTENT | ✅ QA | Verify | Verify all statistics cited | Week 6 | Accuracy critical | FALSE
CONTENT | ✅ QA | Verify | Verify pricing is current | Week 6 | Update if changed | FALSE
CONTENT | ✅ QA | Format | Check internal links open same tab | Week 7 | External = new tab | TRUE
CONTENT | ✅ QA | Format | Ensure consistent bullet styling | Week 7 | Site-wide | TRUE
CONTENT | ✅ QA | Format | Ensure consistent heading styling | Week 7 | Brand consistency | TRUE
CONTENT | 💬 ENGAGE | Comments | Enable comments on blog posts | Week 5 | If disabled | FALSE
CONTENT | 💬 ENGAGE | Comments | Respond to all existing comments | Week 5 | Show engagement | FALSE
CONTENT | 💬 ENGAGE | CTAs | Add inquiry form to service pages | Week 5 | Increase conversions | FALSE
CONTENT | 💬 ENGAGE | CTAs | Add click-to-call buttons | Week 5 | Mobile-friendly | FALSE
CONTENT | 💬 ENGAGE | Social | Add testimonials to service pages | Week 6 | 3-5 per page | FALSE
CONTENT | 💬 ENGAGE | Social | Create case studies | Week 8 | Privacy-protected | TRUE
PHASE 6 | 🚀 GROWTH | Content | Publish 2-4 posts per month | Month 4+ | 1,500+ words each | TRUE

## Multilingual
Phase | Section | Task | Details / Sub-task | Done | Status
Overview | Goal | Establish teznevisan3.com as the official Teznevisan brand and expand to English market |  |  | FALSE
Overview | Timeline | Complete in 4-6 weeks |  |  | FALSE
Overview | Languages | Persian (Primary) + English (Secondary) |  |  | FALSE
Overview | Strategy | Same domain, subfolder structure (/en/) |  |  | FALSE
Phase 1: Technical Foundation | Week 1: Critical Technical Setup | A. Multilingual Infrastructure |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Install WPML Plugin (or Polylang Free) | Purchase WPML ($39/year) or install Polylang free |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Activate plugin |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Configure Languages | Set Persian as default, add English, choose directory (/en/) |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Save settings |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Language Switcher Setup | Enable in header and footer |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Test language switcher on desktop and mobile |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Use flags or text (e.g., "EN ¦ FA") |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | hreflang Tags Configuration | Verify WPML handles automatically or add manual code |  | FALSE
Phase 1 | A. Multilingual Infrastructure | HTML Lang Attribute | Persian: <html lang="fa" dir="rtl">; English: <html lang="en" dir="ltr"> |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Verify in browser inspector |  |  | FALSE
Phase 1 | A. Multilingual Infrastructure | Test Language Switching | Check URLs, content change, mobile |  | FALSE
Phase 1 | B. Robots.txt Optimization | Update robots.txt with full provided code (including AI crawler allows and priority pages) |  |  | FALSE
Phase 1 | B. Robots.txt Optimization | Save and test teznevisan3.com/robots.txt |  |  | FALSE
Phase 1 | B. Robots.txt Optimization | Verify in Google Search Console |  |  | FALSE
Phase 1 | C. XML Sitemaps | Install & activate Yoast SEO (if not already) |  |  | FALSE
Phase 1 | C. XML Sitemaps | Enable XML sitemaps in Yoast |  |  | FALSE
Phase 1 | C. XML Sitemaps | Verify multilingual sitemaps at sitemap_index.xml |  |  | FALSE
Phase 1 | C. XML Sitemaps | Submit sitemap_index.xml to Google Search Console |  |  | FALSE
Phase 1 | C. XML Sitemaps | Submit sitemap_index.xml to Bing Webmaster Tools |  |  | FALSE
Phase 2: Persian Pages | Week 1-2 | Create Page 1: /official-teznevisan-website/ | Title, URL, content sections, SEO, internal links, schema |  | FALSE
Phase 2 |  | Create Page 2: /about-teznevisan-official-history/ | Title, URL, content, SEO, schema |  | FALSE
Phase 2 |  | Create Page 3: /official-contact-information/ | Title, URL, content, SEO, schema |  | FALSE
Phase 2 |  | Create Page 4: /faq-official-teznevisan/ | Title, URL, content, SEO, schema (20+ Qs) |  | FALSE
Phase 2 |  | Create Page 5: /ai-instructions/ | Title, URL, content, SEO |  | FALSE
Phase 2 |  | Create Page 6: /why-teznevisan3-is-official/ | Title, URL, content, SEO |  | FALSE
Phase 2 |  | Create Page 7: /beware-fake-teznevisan-websites/ | Title, URL, content, SEO |  | FALSE
Phase 2 |  | Homepage Optimization (Persian) | Add official notice banner (provided HTML) |  | FALSE
Phase 2 |  | Homepage Optimization | Update title tag |  | FALSE
Phase 2 |  | Homepage Optimization | Update meta description |  | FALSE
Phase 2 |  | Homepage Optimization | Add keywords meta tag |  | FALSE
Phase 2 |  | Homepage Optimization | Add Organization schema |  | FALSE
Phase 2 |  | Homepage Optimization | Add Website schema |  | FALSE
Phase 2 |  | Homepage Optimization | Update footer official notice |  | FALSE
Phase 3: English Pages | Week 2-3 | Create English Homepage /en/ | Title, content, SEO, schema |  | FALSE
Phase 3 |  | Create /en/official-website/ | Title, content, SEO, schema |  | FALSE
Phase 3 |  | Create /en/about-history/ | Title, content, SEO |  | FALSE
Phase 3 |  | Create /en/contact/ | Title, content (highlight Maziyar), SEO |  | FALSE
Phase 3 |  | Create /en/english-coordinator/ | Maziyar page, bio, photo, content, SEO, Person schema |  | FALSE
Phase 3 |  | Create /en/services/ | Services overview grid, content, SEO |  | FALSE
Phase 3 |  | Create /en/services/master-thesis/ | Content, process, SEO |  | FALSE
Phase 3 |  | Create /en/services/statistical-analysis/ | Content, supported software, SEO |  | FALSE
Phase 3 |  | Create /en/faq/ | Content, sections, SEO, schema |  | FALSE
Phase 3 |  | Create /en/ai-instructions/ | Content, SEO |  | FALSE
Phase 4: llms.txt Optimization | Week 3 | Update llms.txt | Add official verification section at top (provided text) |  | FALSE
Phase 4 |  | Update llms.txt | Include English page links |  | FALSE
Phase 4 |  | Update llms.txt | Save and verify https://teznevisan3.com/llms.txt |  | FALSE
Phase 4 |  | Update llms.txt | Validate at https://llmstxt.org/ |  | FALSE
Phase 5: On-Page SEO | Week 3-4 | A. All Service Pages | Update title pattern, H1, breadcrumbs, internal links, schema |  | FALSE
Phase 5 |  | B. Internal Linking Strategy | Implement links from homepage, service pages, blog posts, cross-language |  | FALSE
Phase 5 |  | C. Image Optimization | Create official badges/seals |  | FALSE
Phase 5 |  | C. Image Optimization | Compress all images, add descriptive filenames & ALT text |  | FALSE
Phase 5 |  | C. Image Optimization | Add badges to key locations |  | FALSE
Phase 5 |  | D. URL Structure Audit | Ensure clean, keyword-rich URLs for all pages |  | FALSE
Phase 5 |  | E. Meta Tags Checklist | Add proper title, description, OG tags, Twitter cards to every page |  | FALSE
Phase 5 |  | F. Heading Structure | One H1, logical H2/H3 hierarchy on every page |  | FALSE
Phase 6: Technical SEO | Week 4 | A. Page Speed Optimization | Install caching plugin (WP Rocket preferred) |  | FALSE
Phase 6 |  | A. Page Speed Optimization | Enable caching, minify, image optimization, lazy load |  | FALSE
Phase 6 |  | A. Page Speed Optimization | (Optional) Set up Cloudflare CDN |  | FALSE
Phase 6 |  | A. Page Speed Optimization | Database optimization (WP-Optimize) |  | FALSE
Phase 6 |  | A. Page Speed Optimization | Achieve 80+ mobile / 90+ desktop in PageSpeed Insights |  | FALSE
Phase 6 |  | B. Mobile Optimization | Test & fix mobile responsiveness, tap targets, viewport |  | FALSE
Phase 6 |  | C. SSL/HTTPS | Verify active, force HTTPS, add redirect in .htaccess |  | FALSE
Phase 6 |  | D. XML Sitemap Configuration | Configure Yoast sitemap settings, verify generation |  | FALSE
Phase 6 |  | E. Structured Data | Add all specified schemas (Organization, FAQ, Service, Person, etc.) |  | FALSE
Phase 6 |  | E. Structured Data | Test every page in Google Rich Results Test |  | FALSE
Phase 6 |  | F. Core Web Vitals | Check & optimize LCP, FID, CLS in Search Console |  | FALSE
Phase 7: Content Strategy | Week 4-5 | A. Persian Blog Posts | Publish 10 planned posts (list provided) |  | FALSE
Phase 7 |  | B. English Blog Posts | Publish 8 planned posts (list provided) |  | FALSE
Phase 7 |  | C. Content Optimization | Every post: keyword use, internal links, images, meta, CTA |  | FALSE
Phase 8: Off-Page SEO | Week 5-6 | A. Business Directory Listings | Submit consistent NAP to 5+ Iranian + 3+ international directories |  | FALSE
Phase 8 |  | B. Social Media | Optimize LinkedIn company page |  | FALSE
Phase 8 |  | B. Social Media | Optimize Telegram @Thesissupport |  | FALSE
Phase 8 |  | B. Social Media | Set up WhatsApp Business |  | FALSE
Phase 8 |  | C. Testimonials | Create /testimonials/ and /en/testimonials/ pages, collect & display |  | FALSE
Phase 8 |  | D. Backlink Strategy | Guest posting, resource page outreach, forum participation |  | FALSE
Phase 9: Monitoring Setup | Week 6 | A. Google Search Console | Verify domain, submit sitemaps, request indexing for priority pages |  | FALSE
Phase 9 |  | B. Google Analytics 4 | Install GA4, configure events/conversions, link to Search Console |  | FALSE
Phase 9 |  | C. Bing Webmaster Tools | Verify site, submit sitemap |  | FALSE
Phase 10: AI Discovery | Week 6-7 | Send submission emails to Perplexity, OpenAI, Anthropic (use provided templates) |  |  | FALSE
Phase 10 |  | Verify Google-Extended & Bing allowed in robots.txt |  |  | FALSE
Phase 11: Monitoring & Maintenance | Ongoing | Set up weekly & monthly monitoring routine (GSC, GA4, AI crawlers, rankings) |  |  | FALSE
Final Summary Checklist | Technical Foundation | WPML/Polylang, hreflang, robots.txt, sitemaps, SSL, speed |  |  | FALSE
Final Summary Checklist | Persian Pages | All 7 key pages + homepage/footer optimization |  |  | FALSE
Final Summary Checklist | English Pages | All 10 key pages + language switcher working |  |  | FALSE
Final Summary Checklist | llms.txt & AI | Updated, validated, submitted to major AI systems |  |  | FALSE
Final Summary Checklist | Content & SEO | Blog posts published, on-page optimization complete |  |  | FALSE
Final Summary Checklist | Monitoring | GSC, GA4, Bing set up and monitored |  |  | FALSE
Final Summary Checklist | External Signals | Directory listings, social active, testimonials displayed |  |  | FALSE